## Slide 1
Document number | Column2 | Column3 | … | Planned Issue Date | Actual Issue Date
Test Document 01 |  |  |  | 2020-01-01 | 2020-01-10
Test Document 02 |  |  |  | 2020-01-08 | 2020-01-10
Test Document 03 |  |  |  | 2020-01-15 | 2020-01-10
Test Document 04 |  |  |  | 2020-01-22 | 2020-01-10
Test Document 05 |  |  |  | 2020-01-29 | 2020-02-10
Test Document 06 |  |  |  | 2020-02-05 | 2020-02-10
Test Document 07 |  |  |  | 2020-02-12 | 2020-02-10
Test Document 08 |  |  |  | 2020-02-19 | 2020-02-10
Test Document 09 |  |  |  | 2020-02-26 | 2020-04-10
Test Document 10 |  |  |  | 2020-03-04 | 2020-04-10
Test Document 11 |  |  |  | 2020-03-11 | 2020-04-10
Test Document 12 |  |  |  | 2020-03-18 | 2020-04-10
Test Document 13 |  |  |  | 2020-03-25 | 
Test Document 14 |  |  |  | 2020-04-01 | 
Test Document 15 |  |  |  | 2020-04-08 | 
Test Document 16 |  |  |  | 2020-04-15 | 
Test Document 17 |  |  |  | 2020-04-22 | 
Test Document 18 |  |  |  | 2020-04-29 | 
Test Document 19 |  |  |  | 2020-05-06 | 
Test Document 20 |  |  |  | 2020-05-13 | 
Test Document 21 |  |  |  | 2020-05-20 | 
Test Document 22 |  |  |  | 2020-05-27 | 
Test Document 23 |  |  |  | 2020-06-03 | 
Weeks | Total number of documents | Planned number to Issue | Number of documents Issued
01-Jan-20 | 23 | 1 | 0
08-Jan-20 | 23 | 2 | 0
15-Jan-20 | 23 | 3 | 4
22-Jan-20 | 23 | 4 | 4
29-Jan-20 | 23 | 5 | 4
05-Feb-20 | 23 | 6 | 4
12-Feb-20 | 23 | 7 | 8
19-Feb-20 | 23 | 8 | 8
26-Feb-20 | 23 | 9 | 8
04-Mar-20 | 23 | 10 | 8
11-Mar-20 | 23 | 11 | 8
18-Mar-20 | 23 | 12 | 8
25-Mar-20 | 23 | 13 | 8
01-Apr-20 | 23 | 14 | 8
08-Apr-20 | 23 | 15 | 8
15-Apr-20 | 23 | 16 | 12
22-Apr-20 | 23 | 17 | 12
29-Apr-20 | 23 | 18 | 12
06-May-20 | 23 | 19 | 12
13-May-20 | 23 | 20 | 12
20-May-20 | 23 | 21 | 12
27-May-20 | 23 | 22 | 12
03-Jun-20 | 23 | 23 | 
Chart: 
| 43831 | 43838 | 43845 | 43852 | 43859 | 43866 | 43873 | 43880 | 43887 | 43894 | 43901 | 43908 | 43915 | 43922 | 43929 | 43936 | 43943 | 43950 | 43957 | 43964 | 43971 | 43978 | 43985
Total number of documents | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
Planned number to Issue | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Number of documents Issued | 0 | 0 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Existing Data (Input)
Date needs to be changed to a seperate able as below (Output)
Dates:
There should be possibility to set start date (or week) and end date (or week) somewhere
Then dates are populated week wise
Total number of documents:
Unique count of the items/documents
Planned number to Issue:
Number of documents with planned issue date, less than or equal to the date in the Weeks column
Number of documents Issued:
Number of documents with Actual Issued Date, less than or equal to the date in the Weeks column, if blank do not count
Simple graph from above table